## Task Tracker
JDBC Class Library Project - Task Tracker
Group Number: EOS Group 1
Task | Assigned To | Priority | Status | Due Date | Notes | AI Tool Used (Footnote)
Andrew — Project Manager / Team Lead
Set up GitHub repository | Andrew | High | Completed
Create project folder structure | Andrew | High | Completed
Delegate tasks to team members | Andrew | High | Completed
Manage to-do list and timeline | Andrew | Medium | Completed
Coordinate video editing (MP4) | Andrew | Medium | Completed
Submit final project (GitHub + zip link) | Andrew | High | Completed
Andrew (This is temporary for the case that we are down a partner) — JDBC Core (Connection & Setup)
Create DatabaseConnection.java | Andrew | High | Completed
Implement connection pooling | Andrew | High | Completed
Build ConnectionConfig.java (DB settings) | Andrew | Medium | Completed
Error handling & exception classes | Andrew | Medium | Completed
Write unit tests for connection classes | Andrew | Medium | Completed
Document connection setup classes | Andrew | Medium | Completed
Amrin — JDBC Core (CRUD Operations)
Create GenericDAO.java (base CRUD) | Amrin | High | Completed
Implement CREATE operations | Amrin | High | Completed
Implement READ operations (single & list) | Amrin | High | Completed
Implement UPDATE operations | Amrin | High | Completed
Implement DELETE operations | Amrin | High | Completed
Write unit tests for CRUD classes | Amrin | Medium | Completed
Document CRUD classes | Amrin | Medium | Completed
Andrew— UI Development
Design UI wireframe/mockup | Andrew | High | Completed
Build main application window | Andrew | High | Completed
Create forms for CRUD operations | Andrew | High | Completed
Connect UI to JDBC library | Andrew | High | Completed
Polish styling and layout | Andrew | Medium | Completed
Test UI with live database | Andrew | Medium | Completed
Andrew — Documentation & Testing
Write README.md for the project | Andrew | High | Completed
Document all classes with Javadoc | Andrew | High | Completed
Create user guide for the library | Andrew | Medium | Completed
Integration testing across all modules | Andrew | High | Completed
Document prompt engineering techniques | Andrew | Medium | Completed
Write NACE competencies reflection | Andrew | Medium | Completed
GROUP — Shared Tasks
Record individual video segments | Everyone | High | Completed
Consolidate into 15-20 min YouTube video | Andrew | High | Completed
Final review and testing | Everyone | High | Completed
Upload to YouTube | Andrew | High | Completed